## types
Front End Estimation
Types of Work	Effort minimum unit is ¼ day ~ 2 uninterrupted hours
	How many actual meeting free hours do team members get per day?					Requirements and Design Documents:
					links to documents here
Changes to existing		S	M	L
		99	198	396	Effort In ¼ days
	Coupled Items:	1 to 3	4 to 6	7 or more
	Added Unit tests 80% covered
	Static Analysis - Eslint/SonarCube/SAST/NexusIQ
	Added Snapshots
	Added Storybook states
	PropTypes additions
	Render changes
	Styling M/T/D
	Typography M/T/D
	Accessibility
	Validation Logic
	Events handling
	Refactor
	Peer Review
		S	M	L
New Component		98	196	392
	Coupled Items:	1 to 3	4 to 6	7 or more
	Unit tests 80%+ covered
	Static Analysis - Eslint/SonarCube/SAST/NexusIQ
	Snapshot tests min/max
	Storybook states
	PropTypes
	Render
	Loading/Errors
	Styling M/T/D
	Typography M/T/D
	Accessibility
	Validation Logic
	Events handling
	Lockout/debounce to prevent multiple submissions
	Refactor
	JSDoc
	Peer Review
New API		97	145.5	194
	Data Items:	1 to 3	4 to 6	7 or more
	Unit tests 90%+ covered
	Static Analysis - Eslint/SonarCube/SAST/NexusIQ
	Mock Data Ok/Error
	Fetch.then
	Catch errors
	mockFetch/delay
	Action+Reducer to update app state
	JSDoc
	Peer Review
Design/Layout	Effort	90	135	180
	Sections or Areas:	1 to 3	4 to 6	7 or more
	Risk, not Effort:	1	1.5	3
	If designs exist for all sizes M/T/D = Small risk
	If designs exist for one size only = Large risk
	If designs exist for two sizes only = Mid risk
	Snapshot tests
	Storybook states
	Cypress snapshots M/T/D
	Show/Hide by M/T/D
	Rearrange by M/T/D
	Styling M/T/D
	Refactor
	Peer Review
New Page		96	144	192
	Sections or Areas:	1 to 3	4 to 6	7 or more
	Unit tests 80%+ covered
	Static Analysis - Eslint/SonarCube/SAST/NexusIQ
	Snapshot tests min/max
	Storybook states
	Cypress tests
	Cypress snapshots M/T/D
	Routes
	PropTypes
	Configuration of show/hidden sections and copy text variations
	Render
	Loading/Errors
	Styling M/T/D
	Accessibility/Focus/Tabs
	Events handling between sections
	Refactor
	Peer Review
Configuration		95	142.5	190
	Data Items:	up to 10	10 to 20	30 or more
	Unit tests 100% covered
	Static Analysis - Eslint/SonarCube/SAST/NexusIQ
	Helper functions
	JSDoc
	Peer Review
Logic		94	282	846
	Data Items * States	up to 12	13 to 24	25 or more
	Unit tests 100% covered
	Static Analysis - Eslint/SonarCube/SAST/NexusIQ
	Coding of logic
	Refactor
	JSDoc
	Peer Review

The first tab is meant to be used with the developers to establish what the units of work are and give an estimate of how much effort is needed for a Small, Medium or Large unit of each work type. We restrict effort to a minimum of ¼ day.

The screen tabs would be used for each screen in order to determine what the actual work is.
This would require the side by side designs for each screen possibility, or at least the design showing the journey page flow, so we can see how to divide the components.
We copy the last screen tab just before the final tab before filling in a new page, this then copies the cumulative effort to the next tab.
Each tab should relate to a JIRA ticket for a story/epic and would list the tasks needed once we discovered them. It also contains an uncertainty percentage score to express any unknowns about the page.
This could be filled out with the team so everyone knows how it will be split, or it could just be a few senior leads to speed things up.

The final tab takes the cumulative effort from each screen tab and works out a calendar end date based on how many team members we have, number of hours of meetings per day, number of bank holidays per year and a team load factor.

## screen
Front End Estimation					Estimated Effort	0.0		List of tasks:
Effort for Screen [NAME]					Cumulative	0.0
JIRA-NNNN					Screen	1
	←put 1 in S/M or L column only
	other cells indicate the number of S/M/orL items of given type on the page.
					Effort	Uncertainty
		S	M	L	0	0.0
New Screen? Or					0
Changes to Existing					0
Configuration					0
Logic					0
New Components					0
New APIs needed					0
Design/Layout Effort					0
Design Risk					0
Other					0

Uncertainty					0%

Assumptions

Risks

## screen_2
Front End Estimation					Estimated Effort	90.0		List of tasks:
Effort for Screen [NAME2]					Cumulative	0.0	check that this points to previous screen tab
JIRA-NNNN					Screen	2	check that this points to previous screen tab
	←put 1 in S/M or L column only
	other cells indicate the number of S/M/orL items of given type on the page.
					Effort	Uncertainty
		S	M	L	90	90.0
New Screen? Or					0
Changes to Existing					0
Configuration					0
Logic					0
New Components					0
New APIs needed					0
Design/Layout Effort		1			90
Design Risk					0
Other					0

Uncertainty					0%

Assumptions

Risks

## Final
Front End Estimation			2023-03-23	Today
Cumulative effort for all screens			2023-04-10	Projected End Date

Load Factor	1	i.e. if entire team split between two projects then this would be 2

Screens	2	make sure this points to tab for last screen/page
Cumulative	90.0	make sure this points to tab for last screen/page
Total Effort	90	days
Team Size	10
Meetings	2	hours per day
Work Day	8	hours
Usable Hours	6	hours
Work Days	5	per week
Holidays	20	days per year

Team Effort	72.0	hours
Effective Days	12.0	days ===>	2.4	weeks
Calendar Days	18.5	days
Team Calendar Weeks	2.6	weeks