## types
Front End Estimation
Types of Work | Effort minimum unit is ¼ day ~ 2 uninterrupted hours
| How many actual meeting free hours do team members get per day? |  |  |  |  | Requirements and Design Documents:
links to documents here
Changes to existing |  | S | M | L
|  | 99 | 198 | 396 | Effort In ¼ days
| Coupled Items: | 1 to 3 | 4 to 6 | 7 or more
Added Unit tests 80% covered
Static Analysis - Eslint/SonarCube/SAST/NexusIQ
Added Snapshots
Added Storybook states
PropTypes additions
Render changes
Styling M/T/D
Typography M/T/D
Accessibility
Validation Logic
Events handling
Refactor
Peer Review
|  | S | M | L
New Component |  | 98 | 196 | 392
| Coupled Items: | 1 to 3 | 4 to 6 | 7 or more
Unit tests 80%+ covered
Static Analysis - Eslint/SonarCube/SAST/NexusIQ
Snapshot tests min/max
Storybook states
PropTypes
Render
Loading/Errors
Styling M/T/D
Typography M/T/D
Accessibility
Validation Logic
Events handling
Lockout/debounce to prevent multiple submissions
Refactor
JSDoc
Peer Review
New API |  | 97 | 145.5 | 194
| Data Items: | 1 to 3 | 4 to 6 | 7 or more
Unit tests 90%+ covered
Static Analysis - Eslint/SonarCube/SAST/NexusIQ
Mock Data Ok/Error
Fetch.then
Catch errors
mockFetch/delay
Action+Reducer to update app state
JSDoc
Peer Review
Design/Layout | Effort | 90 | 135 | 180
| Sections or Areas: | 1 to 3 | 4 to 6 | 7 or more
| Risk, not Effort: | 1 | 1.5 | 3
If designs exist for all sizes M/T/D = Small risk
If designs exist for one size only = Large risk
If designs exist for two sizes only = Mid risk
Snapshot tests
Storybook states
Cypress snapshots M/T/D
Show/Hide by M/T/D
Rearrange by M/T/D
Styling M/T/D
Refactor
Peer Review
New Page |  | 96 | 144 | 192
| Sections or Areas: | 1 to 3 | 4 to 6 | 7 or more
Unit tests 80%+ covered
Static Analysis - Eslint/SonarCube/SAST/NexusIQ
Snapshot tests min/max
Storybook states
Cypress tests
Cypress snapshots M/T/D
Routes
PropTypes
Configuration of show/hidden sections and copy text variations
Render
Loading/Errors
Styling M/T/D
Accessibility/Focus/Tabs
Events handling between sections
Refactor
Peer Review
Configuration |  | 95 | 142.5 | 190
| Data Items: | up to 10 | 10 to 20 | 30 or more
Unit tests 100% covered
Static Analysis - Eslint/SonarCube/SAST/NexusIQ
Helper functions
JSDoc
Peer Review
Logic |  | 94 | 282 | 846
| Data Items * States | up to 12 | 13 to 24 | 25 or more
Unit tests 100% covered
Static Analysis - Eslint/SonarCube/SAST/NexusIQ
Coding of logic
Refactor
JSDoc
Peer Review
The first tab is meant to be used with the developers to establish what the units of work are and give an estimate of how much effort is needed for a Small, Medium or Large unit of each work type. We restrict effort to a minimum of ¼ day.
The screen tabs would be used for each screen in order to determine what the actual work is.
This would require the side by side designs for each screen possibility, or at least the design showing the journey page flow, so we can see how to divide the components.
We copy the last screen tab just before the final tab before filling in a new page, this then copies the cumulative effort to the next tab.
Each tab should relate to a JIRA ticket for a story/epic and would list the tasks needed once we discovered them. It also contains an uncertainty percentage score to express any unknowns about the page.
This could be filled out with the team so everyone knows how it will be split, or it could just be a few senior leads to speed things up.
The final tab takes the cumulative effort from each screen tab and works out a calendar end date based on how many team members we have, number of hours of meetings per day, number of bank holidays per year and a team load factor.

## screen
Front End Estimation |  |  |  |  | Estimated Effort | 0 | List of tasks:
Effort for Screen [NAME] |  |  |  |  | Cumulative | 0
JIRA-NNNN |  |  |  |  | Screen | 1
←put 1 in S/M or L column only
other cells indicate the number of S/M/orL items of given type on the page.
[5 empty] | Effort | Uncertainty
|  | S | M | L | 0 | 0
New Screen? Or |  |  |  |  | 0
Changes to Existing |  |  |  |  | 0
Configuration |  |  |  |  | 0
Logic |  |  |  |  | 0
New Components |  |  |  |  | 0
New APIs needed |  |  |  |  | 0
Design/Layout Effort |  |  |  |  | 0
Design Risk |  |  |  |  | 0
Other |  |  |  |  | 0
Uncertainty |  |  |  |  | 0%
Assumptions
Risks

## screen_2
Front End Estimation |  |  |  |  | Estimated Effort | 90 |  | List of tasks:
Effort for Screen [NAME2] |  |  |  |  | Cumulative | 0 | check that this points to previous screen tab
JIRA-NNNN |  |  |  |  | Screen | 2 | check that this points to previous screen tab
←put 1 in S/M or L column only
other cells indicate the number of S/M/orL items of given type on the page.
[5 empty] | Effort | Uncertainty
|  | S | M | L | 90 | 90
New Screen? Or |  |  |  |  | 0
Changes to Existing |  |  |  |  | 0
Configuration |  |  |  |  | 0
Logic |  |  |  |  | 0
New Components |  |  |  |  | 0
New APIs needed |  |  |  |  | 0
Design/Layout Effort |  | 1 |  |  | 90
Design Risk |  |  |  |  | 0
Other |  |  |  |  | 0
Uncertainty |  |  |  |  | 0%
Assumptions
Risks

## Final
Front End Estimation |  |  | 2023-03-23 | Today
Cumulative effort for all screens |  |  | 2023-04-10 11:05 | Projected End Date
Load Factor | 1 | i.e. if entire team split between two projects then this would be 2
Screens | 2 | make sure this points to tab for last screen/page
Cumulative | 90 | make sure this points to tab for last screen/page
Total Effort | 90 | days
Team Size | 10
Meetings | 2 | hours per day
Work Day | 8 | hours
Usable Hours | 6 | hours
Work Days | 5 | per week
Holidays | 20 | days per year
Team Effort | 72 | hours
Effective Days | 12 | days ===> | 2.4 | weeks
Calendar Days | 18.4615 | days
Team Calendar Weeks | 2.6374 | weeks