## types
Front End Estimation
Types of Work | Effort minimum unit is ¼ day ~ 2 uninterrupted hours
How many actual meeting free hours do team members get per day?
Changes to existing |  | S | M | L
|  | 99 | 198 | 396 | Effort In ¼ days
| Coupled Items: | 1 to 3 | 4 to 6 | 7 or more
Added Unit tests 80% covered
Added Snapshots
Added Storybook states
PropTypes additions
Render changes
Styling M/T/D
Typography M/T/D
Accessibility
Validation Logic
Events handling
Refactor
|  | S | M | L
New Component |  | 98 | 196 | 392
| Coupled Items: | 1 to 3 | 4 to 6 | 7 or more
Unit tests 80%+ covered
Snapshot tests min/max
Storybook states
PropTypes
Render
Loading/Errors
Styling M/T/D
Typography M/T/D
Accessibility
Validation Logic
Events handling
Lockout/debounce to prevent multiple submissions
Refactor
JSDoc
New API |  | 97 | 145.5 | 194
| Data Items: | 1 to 3 | 4 to 6 | 7 or more
Unit tests 90%+ covered
Mock Data Ok/Error
Fetch.then
Catch errors
mockFetch/delay
Action+Reducer to update app state
JSDoc
Design/Layout | Effort | 90 | 135 | 180
| Sections or Areas: | 1 to 3 | 4 to 6 | 7 or more
| Risk, not Effort: | 1 | 0.66667 | 0.33333
If designs exist for all sizes M/T/D = S
If designs exist for one size only = L
If designs exist for two sizes only = M
Snapshot tests
Storybook states
Cypress snapshots M/T/D
Show/Hide by M/T/D
Rearrange by M/T/D
Styling M/T/D
Refactor
New Page |  | 96 | 144 | 192
| Sections or Areas: | 1 to 3 | 4 to 6 | 7 or more
Unit tests 80%+ covered
Snapshot tests min/max
Storybook states
Cypress tests
Cypress snapshots M/T/D
Routes
PropTypes
Configuration of show/hidden sections and copy text variations
Render
Loading/Errors
Styling M/T/D
Accessibility/Focus/Tabs
Events handling between sections
Refactor
Configuration |  | 95 | 142.5 | 190
| Data Items: | up to 10 | 10 to 20 | 30 or more
Unit tests 100% covered
Helper functions
JSDoc
Logic |  | 94 | 282 | 846
| Data Items * States | up to 12 | 13 to 24 | 25 or more
Unit tests 100% covered
Coding of logic
Refactor
JSDoc

## screen
Front End Estimation |  |  |  |  | Estimated Effort | 0
Effort for Screen [NAME] |  |  |  |  | Cumulative | 0
←put 1 in S/M or L column only
other cells indicate the number of S/M/orL items of given type on the page.
[5 empty] | Effort | Uncertainty
|  | S | M | L | 0 | 0
New Screen? Or |  |  |  |  | 0
Changes to Existing |  |  |  |  | 0
Configuration |  |  |  |  | 0
Logic |  |  |  |  | 0
New Components |  |  |  |  | 0
New APIs needed |  |  |  |  | 0
Design/Layout Effort |  |  |  |  | 0
Design Risk |  |  |  |  | 0
Other |  |  |  |  | 0
Uncertainty |  |  |  |  | 0%
Assumptions
Risks

## screen_2
Front End Estimation |  |  |  |  | Estimated Effort | 0
Effort for Screen [NAME2] |  |  |  |  | Cumulative | 0
←put 1 in S/M or L column only
other cells indicate the number of S/M/orL items of given type on the page.
[5 empty] | Effort | Uncertainty
|  | S | M | L | 0 | 0
New Screen? Or |  |  |  |  | 0
Changes to Existing |  |  |  |  | 0
Configuration |  |  |  |  | 0
Logic |  |  |  |  | 0
New Components |  |  |  |  | 0
New APIs needed |  |  |  |  | 0
Design/Layout Effort |  |  |  |  | 0
Design Risk |  |  |  |  | 0
Other |  |  |  |  | 0
Uncertainty |  |  |  |  | 0%
Assumptions
Risks

## Final
Front End Estimation |  |  | 2023-03-21 | Today
Cumulative effort for all screens |  |  | 2023-03-21 | Projected End Date
Load Factor | 1 | i.e. if entire team split between two projects then this would be 2
Cumulative | 0 | make sure this points to tab for last screen/page
Total Effort | 0 | days
Team Size | 10
Meetings | 2 | hours per day
Work Day | 8 | hours
Usable Hours | 6 | hours
Work Days | 5 | per week
Holidays | 20 | days per year
Team Effort | 0 | hours
Effective Days | 0 | days
Calendar Days | 0 | days
Team Weeks | 0 | weeks